## Bug Report
| Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date | Assigned To | Environment | Browser/Device | Operating System | Module/Feature | Attachments/Links | Comments | Fixed In Version | Retested By | Retested Date | Regression Status | Test Case ID (if any)
BUG-01 | System accepts negative amount in withdrawal | When attempting to withdraw a negative amount (e.g., -100), the system does not display an error and proceeds with the withdrawal, which violates business logic and could cause financial discrepancies. | 1. Login as Manager 2. Navigate to Withdraw page 3. Enter a valid account number 4. Enter -100 in the Amount field 5. Enter a description 6. Click Submit | The system should display an error message: "Amount must be greater than zero" and should not process the withdrawal | The system accepts the negative amount and proceeds with the withdrawal | High | High | New | [Your Name] | 2025-06-22 |  | UAT | Chrome 125 / PC | Windows 10 | Withdrawal Module | Screenshot: 4d7b9227-ea35-4a73-afcf-560e53f12d76.png | Validation on Amount field may be missing or not triggered properly |  |  |  | Not Tested | TC004
BUG-02 | PIN field prevents entering more than 6 digits without showing any validation message | The PIN field restricts input of more than 6 digits However, when the user attempts to enter more than 6 digits, the system silently blocks further input without displaying any validation or guidance message. This behavior may confuse users, as there is no indication of the input limit. | 1. Open Add New Customer page 2. Enter 6 digits in the PIN field 3. Try to enter an additional digit | System should display a clear validation message such as: “PIN cannot exceed 6 digits” | System prevents additional input No validation or error message is displayed | Medium | Medium | New | Nada Ahmed | 2026-02-06 |  | UAT | Google Chrome | Windows 10 | Add new customer |  | No validation message is displayed when the user exceeds the maximum PIN length. |  |  |  | Not Tested | TC022
BUG-03 | PIN is displayed in plain text in Edit Customer page | The PIN field is displayed in plain text on the Edit Customer page. Since PIN is considered sensitive data, it should be masked to prevent unauthorized access and data exposure. Displaying the PIN openly violates security and data protection standards. | 1. Open Edit Customer page 2. Search for an existing customer 3. Observe the PIN field | PIN should be masked (e.g. ******) Sensitive data should not be visible in plain text | PIN is displayed in plain text and fully visible | High | High | Fixed | Nada Ahmed | 2026-02-06 |  | UAT | Google Chrome | Windows 10 | Add new customer |  | PIN is sensitive information and should be masked to prevent data exposure and unauthorized access. | 3 |  | 2026-02-07 | Done | TC088
BUG-04 | System doesn't display the Balance of the customer that i entered his Account Number | when i go to Balance Enquiry page and typed a Correct Account numbers for a customers i had created, it didn't dispaly the balance of this account and went to a page that says that " This page isn't working right now" | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type a valid account number {179497 , 179498} 3- Click on Submit button | System dispalys the Balance of this account | It redirected me to a page that says " This page isn't working right now" | High | High | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Balance Enquiry is an important action for a customers | Not Fixed |  | 2026-02-08 |  | TC - BE - 037
BUG-05 | System doesn't accept numbers more than 10 digits for Account Number feild and it should accept numers till 16 digits | when i go to Balance Enquiry page and entered an account number that contains 17 digits it accepts only 10 and reject the others then say this account doesn't exist | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type an invalid account number {10176026278845996} 3- Click on Submit button | System displays an error message"Account doesn't exist" | It accepts only 10 digits and display an error message "Account does not exist" | Low | High | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - BE - 038
BUG-06 | System dispalys a wrong error message when entering an Account Number with spaces between it | when i go to Balance Enquiry page and entered an account number that contains spaces between digits it says that " Characters are not allowed and it should say that spaces are not allowed" | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type an invalid account number {1 85478} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message " Characters are not allowed" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - BE - 038
BUG-07 | System make a wrong behavior when entering an Account Number Starts with spaces | when i go to Balance Enquiry page and entered an account number starts with space, it ignore the space and display an error message that account doesn't exist | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type an invalid account number {(start with space)5698714} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message"Account doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - BE - 038
BUG-08 | System make a wrong behavior when entering an Account Number with spaces at the end | when i go to Balance Enquiry page and entered an account number ends with space, it ignore the space and display an error message that account doesn't exist | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type an invalid account number {1478521(space at the end)} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message "Account doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - BE - 038
BUG-09 | System accepts less than 8 digits in Account Number feild | When i go to Balance Enquiry page and enter less than 8 digits in account number feild it accepts it and say this account doesn't exist | - Login as a Manager 1- Navigates to Balance Enquiry Page 2- Type an invalid account number {1547898} 3- Click on Submit button | System displays an error message "Invalid Account Number" | System displays an error message "Account doesn't exist" | Low | Medium | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - BE - 038
BUG-10 | System doesn't display the Mini Statement of the customer when i enter a valid Account Number | When i go to the Mini Statement Page and enter a valid account number of an existing customer i supervised on it, it refer me to a page taht says "This page isn't working right now" and doesn't dispaly any statements | - Login as a Manager 1- Navigates to Mini Statement Page 2- Type a valid account number {179497} 3- Click on Submit button | System dispalys a Mini Statement of transactions of this account | It redirected me to a blank page | Low | High | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windoes 10 | Balance Enquiry |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 042
BUG-11 | System doesn't accept numbers more than 10 digits for Account Number feild and it should accept numers till 16 digits | when i go to Mini Statement page and entered an account number that contains 17 digits it accepts only 10 and reject the others then say this account doesn't exist | - Login as a Manager 1- Navigates to Mini Statemen Page 2- Type an invalid account number {10176026278845996} 3- Click on Submit button | System displays an error message " Invalid Account Number" | It accepts only 10 digits and display an error message "Account does not exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windoes 10 | Mini Statement |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 043
BUG-12 | System dispalys a wrong error message when entering an Account Number with spaces between it | when i go to Mini Statement page and entered an account number that contains spaces between digits it says that " Characters are not allowed and it should say that spaces are not allowed" | - Login as aManager 1- Navigates to Mini Statement Page 2- Type an invalid account number {1 85478} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message " Characters are not allowed" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windoes 10 | Mini Statement |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 043
BUG-13 | System makes a wrong behavior when entering an Account Number Start with spaces | when i go to Mini Statement page and entered an account number starts with space, it ignore the space and display an error message that account doesn't exist | - Login as a Manager 1- Navigates to Mini Statement Page 2- Type an invalid account number {(start with space)5698714} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message "Account doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windoes 10 | Mini Statement |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 043
BUG-14 | System make a wrong behavior when enteres an account number end with spaces at the end | when i go to Mini Statement page and entered an account number ends with space, it ignore the space and display an error message that account doesn't exist | - Login as a Manager 1- Navigates to Mini Statement Page 2- Type an invalid account number {1478521(space at the end)} 3- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message "Account doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windoes 10 | Mini Statement |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 043
BUG-15 | System accepts less than 8 digits in Account Number feild | When i go to Mini Statement page and enter less than 8 digits in account number feild it accepts it and say this account doesn't exist | - Login as a Manager 1- Navigates to Mini Statement Page 2- Type an invalid account number {1547898} 3- Click on Submit button | System displays an error message "Invalid Account Number" | System displays an error messagen "Account doesn't exist" | Medium | Medium | ReOpen | Hajar Muhammad | 2026-02-06 |  | UAT | Microsoft Edge | Windows 10 | Mini Statement |  | Check Account Number Validations again | Not Fixed |  | 2026-02-08 |  | TC - MS - 043
BUG-16 | System accepts less than 8 digits in Payer Account Number feild | When i go to fund transfer page and enter less than 8 digits in payer account number it accepts it and show a wrong error message | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type an invalid payer account No { 4895367 } 3- Type a valid payee account No { 179497 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Invalid Payer Account Number " | System displays an error message "Account 4895367" doesn't exist" | Medium | Medium | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 015
BUG-17 | System accepts more than 16 digits in Payer Account Number feild | When i go to fund transfer page and enter more than 16 digits in payer account number it accepts it and show a wrong error message | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type an invalid payer account No { 75395184279532166 } 3- Type a valid payee account No { 179556 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Invalid Payer Account Number" | System displays an error message "Account 75395184279532166 doesn't exist" | Medium | Medium | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 015
BUG-18 | System shows a wrong error message when entering a spaces between Payer Account Number digits | When i go to fund transfer page an enter a payer account number that contains spaces, system shows that characters are not allowed instesd of spaces | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type an invalid payer account No {12365 6} 3- Type a valid payee account No { 179556 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message " Characters are not allowed" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 015
BUG-19 | System shows a wrong error message when entering Payer Account Number starts with space | When i go to fund transfer page an enter a payer account number that start with spaces, system accepts it and said that "No details found for this account" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type an invalid payer account No {(start with space)5698714} 3- Type a valid payee account No { 179556 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System accepts spaces at the end at dispalys an message "Account 5698714 doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 015
BUG-20 | System shows a wrong error message when entering a Payer Account Number ends with spaces | When i go to fund transfer page an enter a payer account number that end with spaces, system accepts it and said that "No details found for this account" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type an invalid payer account No {1478521(space at the end)} 3- Type a valid payee account No { 179556 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System accepts spaces at the end at dispalys an error message "Account 1478521 doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 015
BUG-21 | System accepts less than 8 digits in Payee Account Number feild | When i go to fund transfer page and enter less than 8 digits in Payee account number it accepts it and show a wrong error message | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No { 179555 } 3- Type an invalid payee account No { 0022458 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Invalid Payee Account No " | System displays an error message that "Account 0022458 doesn't exist" | Medium | Medium | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 016
BUG-22 | System accepts more than 16 digits in Payee Account Number feild | When i go to fund transfer page and enter more than 16 digits in payee account number it accepts it and show a wrong error message | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type a valid payee account No { 11554410027845129 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Invalid Payee Account No " | System displays an error message that "Account11554410027845129 doesn't exist" | Medium | Medium | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 016
BUG-23 | System shows a wrong error message when entering Payee Account Number starts with space | When i go to fund transfer page an enter a payee account number that start with spaces, system accepts it and said that "No details found for this account" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type an invalid payee account No { (start with space)5698714 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System accepts spaces at the end at dispalys an error message "Account 5698714 doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 016
BUG-24 | System shows a wrong error message when entering Payee account number ends with spaces | When i go to fund transfer page an enter a payee account number that end with spaces, system accepts it and said that "No details found for this account" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type an invalid payee account No { 1478521(space at the end } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System accepts spaces at the end at dispalys an error message "Account 1478521 doesn't exist" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC FT - 016
BUG-25 | System shows a wrong error message when entering a Payee Account Number contain spaces between digits | When i go to fund transfer page an enter a payee account number that contains spaces, system shows that characters are not allowed instesd of spaces | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a Valid payer account No { 179555} 3- Type an invalid payee account No {1 54789 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | System displays an error message " Spaces are not allowed" | System displays an error message" Characters are not allowed" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 016
BUG-26 | System accepts a Zero Amount in Fund Transfer | When i go to fund transfer page and enter "zero" in amount feild, system accepts it and transfers funds successfully | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type a valid payee account No { 179556} 4- Type an invalid amount { 0 } 5- Type a valid Description 6- Click on Submit button | System displays an error message "Invalid Amount" | It redirected me to a blank Fund Transfer details page | Low | Medium | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 019
BUG-27 | System accepts Negative Amount in Fund Transfer | When i go to fund transfer page and enter "negative value" in amount feild, system accepts it and transfers funds successfully | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type a valid payee account No { 179556} 4- Type an invalid amount { -500 } 5- Type a valid Description 6- Click on Submit button | System displays an error message "Invalid Amount" | It redirected me to a blank Fund Transfer details page | High | High | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 019
BUG-28 | System shows a wrong error message when entering decimals up to more than 2 places in Amount feild | When i go to fund transfer page and enter decimals up to more than 2 places in amount feild, it sows taht special characters are not allowed | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179555} 3- Type a valid payee account No { 179556} 4- Type an invalid amount { 500.023} 5- Type a valid Description 6- Click on Submit button | System dispalys an error message "decimals up to more than 2 places are not allowed" | System dispalys an error message "Special Characters are not allowed" | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 019
BUG-29 | System shows a wrong error message when entering a non-existing Payer Account Number | When i go to fund transfer page and enter a non existing payer account, it shows that "No details found for this accounts" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a invalid payer account No {00000000} 3- Type a valid payee account No { 179497} 4- Type avalid amount {5000} 5- Type a valid Description 6- Click on Submit button | System displays an error message "Payer Account not found" | System displays an error message "Account 00000000 doesn't exist" | Low | Low | Closed | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | V4 |  | 2026-02-08 |  | TC - FT - 021
BUG-30 | System shows a wrong error message when entering a non-existing Payee Account Number | When i go to fund transfer page and enter a non existing payee account, it shows that "No details found for this accounts" | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No {179498} 3- Type an invalid payee account No { 00000000} 4- Type avalid amount {5000} 5- Type a valid Description 6- Click on Submit button | System displays an error message "Payee Account not found" | System displays an error message "Account 00000000 doesn't exist" | Low | Low | Closed | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | V4 |  | 2026-02-08 |  | TC - FT - 022
BUG-31 | Systems accepts more than 100 character in Description feild | When i go to fund transfer page and enter more than 100 character in description feild, system accepts it and transfers funds successfully | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No { 179498 } 3- Type a valid payee account No { 179497 } 4- Type a valid amount { 200} 5- Type more than 100 character in description feild {llllllkkkkkkjjjjhhhhhhhhhhhhhhhhhnnnnnnnnnnnnnnnnnnnnnnnnnnnhhhhhhhhhhbbbbbbbbbboooooooooopppppppppphhhhhhhh} 6- Click on Submit button | System displays an error message "Description exceeds max length" | Description accepts only 20 Character | Low | Low | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 |  | TC - FT - 023
BUG-32 | System accepts that the source and destination Accounts are the same | When i go to fund transfer page and enter the payer account number same as payee account number, system accepts it and fund transferes | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No { 179497 } 3- Type a payee account No the same as payer { 179497 } 4- Type a valid amount { 500} 5- Type a valid Description 6- Click on Submit button | System displays an error message that payer account number and payee account number must not be the same | System displays an error message " payer account number and payee account number must not be the same" | Medium | Medium | Closed | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | V4 |  | 2026-02-08 |  | TC - FT - 024
BUG-33 | System accepts less than minimum length in Change Password feild | When i go to change password page and enter a new password less than minimum length, system accepts it and change password successfully | - Login as a Manager 1- Navigates to Change Pssword Page 2- Type a valid old password 3- Type an invalid new password {Hag$245} 4- Type the same passsword in confirm password feild {Hag$245} 5- Click on Submit button | System dispalys an error message" Password is too short" | Password Changed successfully | Low | High | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Change password |  |  | Not Fixed |  | 2026-02-08 |  | TC - CP - 028
BUG-34 | System accepts more than maximum length in Change Password feild | When i go to change password page and enter a new password more than maximum length, system accepts it and change password successfully | - Login as a Manager 1- Navigates to Change Pssword Page 2- Type a valid old password {Hag$245} 3- Type an invalid new password {hagar@#$!23547896khto} 4- Type the same passsword in confirm password feild {hagar@#$!23547896khto} 5- Click on Submit buttton | System dispalys an error message "Password is too long" | Password Changed successfully | Low | High | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Change password |  |  | Not Fixed |  | 2026-02-08 |  | TC - CP - 028
BUG-35 | System accepts Password that doesn't contain any letters | When i go to change password page and enter a new password taht doesn't have any letters, system accepts it and change the password successfully | - Login as a Manager 1- Navigates to Change Pssword Page 2- Type a valid old password {hagar@#$!23547896khto} 3- Type an invalid new password {753951@#} 4- Type the same passsword in confirm password feild {753951@#} 5- Click on Submit button | System dispaly an error message " Enter at least one character" | Password Changed successfully | Low | High | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Change password |  |  | Not Fixed |  | 2026-02-08 |  | TC - CP - 028
BUG-36 | System allows to use a recent reused Password for a New Password | When i go to change password page and enter a recent old password in a new password feild, system accepts it and change password successfully | - Login as a Manager 1- Navigates to Change Pssword Page 2- Type a valid old password{753951@#} 3- Type a reused old password as a new password {Hag$245} 4- Type the same passsword in confirm password feild {Hag$245} 5- Click on Submit button | System displays an error message " You cannot reuse last 3–5 passwords" | Password Changed successfully | Low | High | ReOpen | Hajar Muhammad | 2026-02-07 |  | UAT | Microsoft Edge | Windows 10 | Change password |  |  | Not Fixed |  | 2026-02-08 |  | TC - CP - 031
BUG-37 | System doesn't display the Fund Transfer details | When i go to Fund Transfer page and enter a valid details it redirected me to a blank / empty Fund Transfer details page | - Login as a Manager 1- Navigate to Fund Transfer Page 2- Type a valid payer account No { 179497 } 3- Type a valid payee account No { 179498 } 4- Type a valid amount { 1 } 5- Type a valid Description 6- Click on Submit button | Funds Transferes successfully | It redirected me to a Fund Transfer details page with no data | High | High | New | Hajar Muhammad | 2026-02-08 |  | UAT | Microsoft Edge | Windows 10 | Fund Transfer |  |  | Not Fixed |  | 2026-02-08 | Fail | TC - FT - 014
BUG-38 | System behaves wrong while entering an Account Number that i'm not superviso on it | When i go to Mini Statement Page and enter Account Number for a customer that not belong to me, it redirected me to blank page instead of displaying an error message that i'm not authorized | - Login as a Manager 1- Navigates to Mini Statement Page 2- Type an account number of a customer you are not supervisor on it {179494} 3- Click on Submit button | System displays an error message " you aren't authorized" | It redirected me to a blank page | Low | Medium | New | Hajar Muhammad | 2026-02-08 |  | UAT | Microsoft Edge | Windows 10 | Mini Statement |  |  | Not Fixed |  | 2026-02-08 | Fail | TC - MS - 045
BUG-39 | in the mini statement page enter valid account number and click on submit button redirected blank page | system is redirected blank page when I enter valid account number in account number field and click submit button | 1- visit mini statement page 2- type "179494" in account number 3- click enter button | user can be redirected to account number page | User is redirected to blank page | high | high | new | Hussien Hamdy | 2026-07-02 |  | UAT | Google Chrome | Windoes 11 | Mini statement | [5 empty] | not tested | TC - MS - 005
BUG-40 | the account number accepted less than 8 digits | in the mini statement page in the number account is accepted less than 8 digits | 1- visit mini statement page 2- type "1234567" in account number 3- click enter button | should be an error message "this number is invalid" | system accepted Less than 8 digits | low | low | new | Hussien Hamdy | 2026-07-02 |  | UAT | Google Chrome | Windoes 11 | Mini statement | [5 empty] | not tested | TC - MS - 003
BUG-41 | system can't be showed the password evry time in the change password | in the change password page can't be showed passwords evry time in old password , new password and confirm password. | 1-visit change password page 2- on the right of the text field 3- click on show password vice verse | should be user can show password and vice verse | user can,t be showed password evry time | low | low | new | Hussien Hamdy | 2026-07-02 |  | UAT | Google Chrome | Windoes 11 | Change password | [5 empty] | not tested | TC-CP-053
BUG-42 | System navigates to HTTP 500 error page when performing action on Edit Customer | When performing an action on the Edit Customer page, the system redirects to an error page showing HTTP ERROR 500. This indicates an internal server error and prevents the user from completing the intended action. | 1. Login to Guru99 Banking application 2. Navigate to Edit Customer page 3. Enter a valid Customer ID 4.Click on the action button Submit. | System should process the request successfully Customer details should be displayed or updated as expected | System redirects to an error page Message displayed: “This page isn’t working – HTTP ERROR 500” | High | High | New | Nada Ahmed | 2026-02-07 |  | UAT | Google Chrome | Windows 10 | Delete Customer |  | HTTP 500 indicates an internal server error. The request is sent successfully, but the server fails to handle it. |  |  |  |  | TC-DC-116
BUG-43 | Customized Statement - Minimum transaction value accepts zero | Minimum Transaction Value field allows entering zero, which is invalid | 1. Login to Guru99 Banking website 2. Navigate to Customized Statement page 3. Enter 0 in Minimum Transaction Value 4. Click Submit | System displays an error: "value must be greater than zero" | System accepts zero value | Low | Medium | Open | Abdelrhman Lotfy | 2026-08-02 |  | UAT | Google Chrome | Windows 10 | Customized Statement |  |  | Not Fixed |  |  | Not Tested | TC-CS-146
BUG-44 | Customized Statement - From Date greater than To Date is accepted | System allows submission when From Date is later than To Date | 1. Login to Guru99 Banking website 2. Navigate to Customized Statement page 3. Enter From Date later than To Date 4. Click Submit | System displays an error: "invalid date range" | Form is submitted without validation | High | High | Open | Abdelrhman Lotfy | 2026-08-02 |  | UAT | Google Chrome | Windows 10 | Customized Statement |  |  | Not Fixed |  |  | Not Tested | TC-CS-144
BUG-45 | Customer has changed paasword of the account number and don't have login with a new password | Customer has changed paasword of the account number and don't have login with a new password and customer can't access the account | 1- visit login page 2- type "1303" in user name 3- type "123456@" in password 4- click on login button | user can be redirected to home page | system show error message " user name or password is in valid " | high | High | NEW | Hussien Hamdy | 2026-08-02 |  | UAT | Google Chrome | Windows 11 | Change password | [5 empty] | Not Tested